## Layout
Thông tin user
Chat box
Nội dung chat
Gửi
Filter region
Group
+ Add group
+ Add user

## Plan
Messenger - CPTH
Yêu cầu
Dự kiến hoàn thành để golive vào tuần thứ 3 của Tháng 3
Tương tự dự án FCNW, nhưng sẽ có thay đổi từ forum -> messenger
Làm trên webview để dễ mở rộng trên PC, android, IOS
Gởi Region - Distributor, User cho TH để xác nhận và dev sẽ tạo sẵn các group theo dữ liệu đó. (Có thể có thêm user là distributor) => Tuần sau gởi cho TH, trước khi gửi book họp với a Đức trước)
Bản Release 1 bao gồm nhưng tính năng nào.
Tính năng
1 | Login | UAT 1
2 | Group | UAT 1
3 | User | UAT 1
4 | Chat | UAT 1
5 | Like/Unlike | UAT 1
6 | View | UAT 2
7 | Top like, Top View | UAT 2
8 | Shortcut Code | UAT 2
9 | Real time | UAT 1
10 | Notifycation | UAT 2
46711
No. | Công việc | Mô tả | Position | Thời gian thực hiện | Thời gian hoàn thành | Độ ưu tiên | Thực hiện | Trạng thái
1 | #46843 Review and fix User data for User preparation | Chuẩn bị danh sách User cho hệ thống Messenger (Danh sách user sẽ dùng trong demo 1) |  | 2020-02-17 | 2020-02-18 |  | Phát | Done
2 | #46843 Review and fix Sales Territory data for Group preparation | Chuẩn bị danh sách group sẽ tạo trên hệ thống |  | 2020-02-17 | 2020-02-18 |  | Phát | Done
3 | Họp với a Đức danh sách User & Group | Đưa danh sách để anh Đức chốt trước khi gửi cho KH. |  | 2020-02-18 | 2020-02-18 |  | Phát | Done
4 | Gởi TH file USER & Group | Gửi mail cho KH |  | 2020-02-18 | 2020-02-19 |  | PA | 19-Feb KH Feedback: Bổ sung thêm user DSR vào mỗi group. Xoá 1 số User ko sử dụng.
I. Giai đoạn phân tích và thiết kế database
5 | Thiết kế DB | Xem lại cấu trúc database của FCNW - Tạo chung database với MMV- CPTH - Các table nên có tiền tố giống nhau để gôm lại gần |  | 2020-02-18 | 2020-02-19 |  | DEV
6 | Book họp với a.Đức về DB | Trình bày DB của hệ thống |  | 2020-02-20 | 2020-02-20 |  | DEV
7 | Chỉnh sửa và hoàn tất thiết kế DB | Chốt chỉnh sửa DB |  | 2020-02-21 | 2020-02-21 |  | DEV
8 | Login | - Sử dụng lại trang login theo framework (IIAT) - User & Password - Lưu đăng nhập | User |  |  |  | Duy
9 | Group | - Tạo/Chỉnh sửa/ Xoá group - Sẽ tạo sẵn theo Region, Distributor. - Group sẽ đồng bộ với master data Distributor - Mỗi group sẽ là 1 table mới để lưu nội dung chat. - Có 1 table để quản lí thông tin group mà user tạo và lưu tên table group. | User |  |  |  | Duy
10 | User | - Loại User: admin, RM,CDS,DSR…. - Phân quyền user thuộc group nào. | User |  |  |  | Duy
11 | Chat | - Nội dung có thể chat: Text, img, emoji icon, video.. - khi load tin nhắn lên thì sẽ qua hàm replace để thay đổi thành IMG, emoji icon, video. | User |  |  |  | Trường
12 | Like/Unlike | - Like/unlike nằm trên từng dòng tin nhắn - Ở tin nhắn sẽ thấy số lượng like - click vào sẽ thấy user nào đã like. | User |  |  |  | Hùng
13 | View | - Số người xem tin nhắn | User |  |  |  | Hùng
14 | Top like, Top View | tạm thời ko làm | User
15 | Shortcut Code | - nhập mã để check doanh số hiện tại của Sales.( theo dạng cú pháp) VD: #TH15S00001 ->> 35,000B | User
16 | Real time | - Nội dung tin nhắn sẽ hiển thị ngay sau khi gửi | User |  |  |  | Hùng
17 | Notifycation | - Hiển thị thông báo khi có tin nhắn mới | User
II. Kiểm tra các tính năng
| III. GO LIVE |  |  |  | 2020-03-16

## Database
|  | M_DISTRIBUTOR va M_REGION Region is type 1, Distributor is type 2 | M_MESS_GROUP | MESS_GROUP_CD | MESS_CODE | MESS_NAME (Hiển thị cho người dùng)
|  |  |  | 1 | 110000 | GROUP_CHUNG
|  |  |  | 2 | 120000 | Group_Chat_ABC
Tính năng | Các table liên quan |  | M_MESS_TABLE_GROUP
Login | - M_USER: thông tin user - S_USRDIST: User và NPP - O_MESS_ROLE_USER: Phân quyền tài khoản - O_MESS_Group_User: Link User và Group |  | MESSENGER_TABLE_GROUP_CD (Tự tăng) | MSS_GROUP_CD | GROUP_TABLE_NAME (Tên table trên DB)
Group | - M_MESS_TABLE_GROUP: Define Group - M_DISTRIBUTOR -> M_MESS_GROUP - M_REGION -> M_MESS_GROUP |  | 1 | 1 | O_MESSAGE_GROUP_<yymmdd_000001>
Chat | - O_MESSAGE_GROUP_<Group_ID>: Lưu nội dung chat trong một group. - M_MESS_TABLE_GROUP: Lưu tên group và table group chat tương ứng - O_MESS_GROUP_VEW_<yymmdd_000001>: Lưu những user đã xem nội dung tin nhắn. |  | 2 | 2 | O_MESSAGE_GROUP_GROUPCHATABC
Notification | - O_NOTIFICATION: Lưu thông báo +) Khi có tin nhắn mới. +) Khi được like tin nhắn.
O_MESS_GROUP_LEVEL
|  |  |  | MESS_GROUP_CD | MESS_GROUP_PARENT_CD
|  |  |  | 2 | 1
|  |  |  | 3 | 1
|  |  |  | 4 | 1
|  |  |  | 5 | 2
O_MESSAGE_GROUP_<yymmdd_000001>
|  |  |  | MESS_CD | USER_CD | MESS_CONTENT | TOTAL_LIKE | ACTIVE ( hide = 0)
|  |  |  | 1 | TRUONG | hi :D | 5 | 1
|  |  |  | 2 | PHAT | Hello | 10 | 0
O_MESS_GROUP_VEW_<yymmdd_000001>
|  |  |  | VIEW_CD | USER_CD | LAST_MESS_CD
[5 empty] | TRUONG | 2
|  |  | M_MESS_USER (đồng bộ từ M_USER và M_SALES) | USER_CD | USER_NAME | USER_PASSWORD | ROLE_TYPE
Add Group
List group
Tên Group
Region
Distributor
SALES

## Group - User
|  | đơn vị nhỏ nhất (group) |  | Summary
Region | DISTRIBUTOR_CODE | DISTRIBUTOR_NAME | USER_USERNAME
BANGKOK | 15290019 | CHANTHABURI DISTRIBUTOR CO.,LTD | admin | Group | Region | 1
|  |  | BANGKOK |  | Distributor | 5
CDM_CPTH
|  |  | FPIT_JU | User |  | 36
|  |  | FPIT_TL |  | admin
| 15290158 | T.B. CONSUMER HOUSE CO.,LTD | admin |  | BANGKOK
|  |  | BANGKOK |  | CDM_CPTH
|  |  | CDM_CPTH |  | FPIT_JU
|  |  | FPIT_CB |  | FPIT_TL
|  |  | FPIT_TL |  | FPIT_CB
| 15290205 | KAOLIN ENTERPRISES CO.,LTD. | admin |  | FPIT_KO
|  |  | BANGKOK |  | FPIT_PD
|  |  | CDM_CPTH |  | FPIT_TP
|  |  | FPIT_KO |  | CENTRAL
|  |  | FPIT_TL |  | FPIT_NP
| 15290212 | P.Y. DISTRIBUTION CO.,LTD | admin |  | FPIT_RB
|  |  | BANGKOK |  | FPIT_PR
|  |  | CDM_CPTH |  | FPIT_NA
|  |  | FPIT_PD |  | FPIT_LB
|  |  | FPIT_TL |  | FPIT_CM
| 15290213 | TP DISTRIBUTION LIMITED PARNERSHIP | admin |  | NORTH
|  |  | BANGKOK |  | rm_user
|  |  | CDM_CPTH |  | FPIT_PY
|  |  | FPIT_TL |  | FPIT_PI
|  |  | FPIT_TP |  | FPIT_KA
FPIT_UD
NORTHEAST
FPIT_SR
FPIT_UB
FPIT_NR
FPIT_SK
FPIT_KH
FPIT_RO
FPIT_SU
SOUTH
FPIT_YA
FPIT_NK
FPIT_TR
FPIT_SO
FPIT_CU

## Detail
Region | DISTRIBUTOR_CODE | DISTRIBUTOR_NAME | USER_USERNAME
NORTHEAST | 15290115 | UBON DISTRIBUTION CO.,LTD | admin | Row Labels | Count of DISTRIBUTOR_CODE
SOUTH | 15290204 | P&Y INTERTRADE 2016 CO., LTD | admin | admin | 27
BANGKOK | 15290213 | TP DISTRIBUTION LIMITED PARNERSHIP | admin | BANGKOK | 6
NORTH | 15290222 | THONGPICCHETKUL LIMITED PARTNERSHIP | admin | CDM_CPTH | 27
CENTRAL | 15290224 | BINBON LORETRADE CO., LTD. | admin | CENTRAL | 4
SOUTH | 15290030 | JOBBER SURAT CO.,LTD. | admin | FPIT_CB | 1
NORTHEAST | 15290185 | GOLD NAKHONRATCHSIMA CO.,LTD | admin | FPIT_CM | 1
CENTRAL | 15290197 | RATTANAPHAIBOON SAMUTSONGKHARM | admin | FPIT_CU | 1
BANGKOK | 15290019 | CHANTHABURI DISTRIBUTOR CO.,LTD | admin | FPIT_JU | 1
BANGKOK | 15290158 | T.B. CONSUMER HOUSE CO.,LTD | admin | FPIT_KA | 1
CENTRAL | 15290171 | R S INTER GROUP CO.,LTD. | admin | FPIT_KH | 1
CENTRAL | 15290206 | STANGRUNGRUEANGKIT CO,.LTD. | admin | FPIT_KO | 1
SOUTH | 15290059 | PHI MARN CONSUMER CO.,LTD. | admin | FPIT_LB | 1
SOUTH | 15290117 | JOBBER SURAT CO,LTD. | admin | FPIT_NA | 1
NORTH | 15290191 | PHRAE PATTAPEE CO,LTD. | admin | FPIT_NK | 1
SOUTH | 15290193 | GOLD 2013 CO.,LTD. | admin | FPIT_NP | 1
NORTHEAST | 15290098 | UDORN ORAN (1997) PART,LTD. | admin | FPIT_NR | 1
NORTHEAST | 15290099 | SURIN PURITY | admin | FPIT_PD | 1
NORTHEAST | 15290189 | AYA INTERTRADE CO.,LTD | admin | FPIT_PI | 1
NORTHEAST | 15290203 | 2009 SIAMTRADING KHONKAEN CO.,LTD. | admin | FPIT_PR | 1
BANGKOK | 15290212 | P.Y. DISTRIBUTION CO.,LTD | admin | FPIT_PY | 1
SOUTH | 15290216 | CHUMPHON 2000 CO., LTD | admin | FPIT_RB | 1
NORTHEAST | 15290218 | HIPER DC CO.,LTD. | admin | FPIT_RO | 1
NORTH | 15290220 | SMIS ONE LTD.PARTNERSHIP (BRANCH 1) | admin | FPIT_SK | 1
CENTRAL | 15290225 | NARA DISTRIBUTION CO.,LTD. | admin | FPIT_SO | 1
NORTH | 15290226 | MAK RUAY SAP CO.,LTD | admin | FPIT_SR | 1
BANGKOK | 15290205 | KAOLIN ENTERPRISES CO.,LTD. | admin | FPIT_SU | 1
BANGKOK | 15290213 | TP DISTRIBUTION LIMITED PARNERSHIP | BANGKOK | FPIT_TL | 28
BANGKOK | 15290019 | CHANTHABURI DISTRIBUTOR CO.,LTD | BANGKOK | FPIT_TP | 1
BANGKOK | 15290158 | T.B. CONSUMER HOUSE CO.,LTD | BANGKOK | FPIT_TR | 1
BANGKOK | 15290205 | KAOLIN ENTERPRISES CO.,LTD. | BANGKOK | FPIT_UB | 1
CENTRAL | 15290206 | STANGRUNGRUEANGKIT CO,.LTD. | BANGKOK | FPIT_UD | 1
BANGKOK | 15290212 | P.Y. DISTRIBUTION CO.,LTD | BANGKOK | FPIT_YA | 1
NORTH | 15290222 | THONGPICCHETKUL LIMITED PARTNERSHIP | CDM_CPTH | NORTH | 5
NORTHEAST | 15290115 | UBON DISTRIBUTION CO.,LTD | CDM_CPTH | NORTHEAST | 7
SOUTH | 15290204 | P&Y INTERTRADE 2016 CO., LTD | CDM_CPTH | rm_user | 1
BANGKOK | 15290213 | TP DISTRIBUTION LIMITED PARNERSHIP | CDM_CPTH | SOUTH | 6
CENTRAL | 15290224 | BINBON LORETRADE CO., LTD. | CDM_CPTH
SOUTH | 15290030 | JOBBER SURAT CO.,LTD. | CDM_CPTH
NORTHEAST | 15290185 | GOLD NAKHONRATCHSIMA CO.,LTD | CDM_CPTH
CENTRAL | 15290197 | RATTANAPHAIBOON SAMUTSONGKHARM | CDM_CPTH
BANGKOK | 15290019 | CHANTHABURI DISTRIBUTOR CO.,LTD | CDM_CPTH
BANGKOK | 15290158 | T.B. CONSUMER HOUSE CO.,LTD | CDM_CPTH
CENTRAL | 15290171 | R S INTER GROUP CO.,LTD. | CDM_CPTH
BANGKOK | 15290205 | KAOLIN ENTERPRISES CO.,LTD. | CDM_CPTH
CENTRAL | 15290206 | STANGRUNGRUEANGKIT CO,.LTD. | CDM_CPTH
SOUTH | 15290059 | PHI MARN CONSUMER CO.,LTD. | CDM_CPTH
SOUTH | 15290117 | JOBBER SURAT CO,LTD. | CDM_CPTH
NORTH | 15290191 | PHRAE PATTAPEE CO,LTD. | CDM_CPTH
SOUTH | 15290193 | GOLD 2013 CO.,LTD. | CDM_CPTH
NORTHEAST | 15290098 | UDORN ORAN (1997) PART,LTD. | CDM_CPTH
NORTHEAST | 15290099 | SURIN PURITY | CDM_CPTH
NORTHEAST | 15290189 | AYA INTERTRADE CO.,LTD | CDM_CPTH
NORTHEAST | 15290203 | 2009 SIAMTRADING KHONKAEN CO.,LTD. | CDM_CPTH
BANGKOK | 15290212 | P.Y. DISTRIBUTION CO.,LTD | CDM_CPTH
SOUTH | 15290216 | CHUMPHON 2000 CO., LTD | CDM_CPTH
NORTHEAST | 15290218 | HIPER DC CO.,LTD. | CDM_CPTH
NORTH | 15290220 | SMIS ONE LTD.PARTNERSHIP (BRANCH 1) | CDM_CPTH
CENTRAL | 15290225 | NARA DISTRIBUTION CO.,LTD. | CDM_CPTH
NORTH | 15290226 | MAK RUAY SAP CO.,LTD | CDM_CPTH
CENTRAL | 15290224 | BINBON LORETRADE CO., LTD. | CENTRAL
CENTRAL | 15290197 | RATTANAPHAIBOON SAMUTSONGKHARM | CENTRAL
CENTRAL | 15290171 | R S INTER GROUP CO.,LTD. | CENTRAL
CENTRAL | 15290225 | NARA DISTRIBUTION CO.,LTD. | CENTRAL
BANGKOK | 15290158 | T.B. CONSUMER HOUSE CO.,LTD | FPIT_CB
NORTH | 15290191 | PHRAE PATTAPEE CO,LTD. | FPIT_CM
SOUTH | 15290216 | CHUMPHON 2000 CO., LTD | FPIT_CU
BANGKOK | 15290019 | CHANTHABURI DISTRIBUTOR CO.,LTD | FPIT_JU
NORTH | 15290230 | THONGPICCHETKUL LIMITED PARTNERSHIP (BR1) | FPIT_KA
NORTHEAST | 15290203 | 2009 SIAMTRADING KHONKAEN CO.,LTD. | FPIT_KH
BANGKOK | 15290205 | KAOLIN ENTERPRISES CO.,LTD. | FPIT_KO
CENTRAL | 15290225 | NARA DISTRIBUTION CO.,LTD. | FPIT_LB
CENTRAL | 15290224 | BINBON LORETRADE CO., LTD. | FPIT_NA
SOUTH | 15290117 | JOBBER SURAT CO,LTD. | FPIT_NK
CENTRAL | 15290171 | R S INTER GROUP CO.,LTD. | FPIT_NP
NORTHEAST | 15290185 | GOLD NAKHONRATCHSIMA CO.,LTD | FPIT_NR
BANGKOK | 15290212 | P.Y. DISTRIBUTION CO.,LTD | FPIT_PD
NORTH | 15290222 | THONGPICCHETKUL LIMITED PARTNERSHIP | FPIT_PI
CENTRAL | 15290206 | STANGRUNGRUEANGKIT CO,.LTD. | FPIT_PR
NORTH | 15290220 | SMIS ONE LTD.PARTNERSHIP (BRANCH 1) | FPIT_PY
CENTRAL | 15290197 | RATTANAPHAIBOON SAMUTSONGKHARM | FPIT_RB
NORTHEAST | 15290218 | HIPER DC CO.,LTD. | FPIT_RO
NORTHEAST | 15290189 | AYA INTERTRADE CO.,LTD | FPIT_SK
SOUTH | 15290204 | P&Y INTERTRADE 2016 CO., LTD | FPIT_SO
NORTHEAST | 15290099 | SURIN PURITY | FPIT_SR
SOUTH | 15290030 | JOBBER SURAT CO.,LTD. | FPIT_SU
NORTHEAST | 15290115 | UBON DISTRIBUTION CO.,LTD | FPIT_TL
SOUTH | 15290204 | P&Y INTERTRADE 2016 CO., LTD | FPIT_TL
BANGKOK | 15290213 | TP DISTRIBUTION LIMITED PARNERSHIP | FPIT_TL
NORTH | 15290222 | THONGPICCHETKUL LIMITED PARTNERSHIP | FPIT_TL
CENTRAL | 15290224 | BINBON LORETRADE CO., LTD. | FPIT_TL
SOUTH | 15290030 | JOBBER SURAT CO.,LTD. | FPIT_TL
NORTHEAST | 15290185 | GOLD NAKHONRATCHSIMA CO.,LTD | FPIT_TL
CENTRAL | 15290197 | RATTANAPHAIBOON SAMUTSONGKHARM | FPIT_TL
BANGKOK | 15290019 | CHANTHABURI DISTRIBUTOR CO.,LTD | FPIT_TL
BANGKOK | 15290158 | T.B. CONSUMER HOUSE CO.,LTD | FPIT_TL
CENTRAL | 15290171 | R S INTER GROUP CO.,LTD. | FPIT_TL
BANGKOK | 15290205 | KAOLIN ENTERPRISES CO.,LTD. | FPIT_TL
CENTRAL | 15290206 | STANGRUNGRUEANGKIT CO,.LTD. | FPIT_TL
SOUTH | 15290059 | PHI MARN CONSUMER CO.,LTD. | FPIT_TL
SOUTH | 15290117 | JOBBER SURAT CO,LTD. | FPIT_TL
NORTH | 15290191 | PHRAE PATTAPEE CO,LTD. | FPIT_TL
SOUTH | 15290193 | GOLD 2013 CO.,LTD. | FPIT_TL
NORTHEAST | 15290098 | UDORN ORAN (1997) PART,LTD. | FPIT_TL
NORTHEAST | 15290099 | SURIN PURITY | FPIT_TL
NORTHEAST | 15290189 | AYA INTERTRADE CO.,LTD | FPIT_TL
NORTHEAST | 15290203 | 2009 SIAMTRADING KHONKAEN CO.,LTD. | FPIT_TL
BANGKOK | 15290212 | P.Y. DISTRIBUTION CO.,LTD | FPIT_TL
SOUTH | 15290216 | CHUMPHON 2000 CO., LTD | FPIT_TL
NORTHEAST | 15290218 | HIPER DC CO.,LTD. | FPIT_TL
NORTH | 15290220 | SMIS ONE LTD.PARTNERSHIP (BRANCH 1) | FPIT_TL
CENTRAL | 15290225 | NARA DISTRIBUTION CO.,LTD. | FPIT_TL
NORTH | 15290226 | MAK RUAY SAP CO.,LTD | FPIT_TL
NORTH | 15290230 | THONGPICCHETKUL LIMITED PARTNERSHIP (BR1) | FPIT_TL
BANGKOK | 15290213 | TP DISTRIBUTION LIMITED PARNERSHIP | FPIT_TP
SOUTH | 15290193 | GOLD 2013 CO.,LTD. | FPIT_TR
NORTHEAST | 15290115 | UBON DISTRIBUTION CO.,LTD | FPIT_UB
NORTHEAST | 15290098 | UDORN ORAN (1997) PART,LTD. | FPIT_UD
SOUTH | 15290059 | PHI MARN CONSUMER CO.,LTD. | FPIT_YA
NORTH | 15290222 | THONGPICCHETKUL LIMITED PARTNERSHIP | NORTH
NORTH | 15290191 | PHRAE PATTAPEE CO,LTD. | NORTH
NORTH | 15290220 | SMIS ONE LTD.PARTNERSHIP (BRANCH 1) | NORTH
NORTH | 15290226 | MAK RUAY SAP CO.,LTD | NORTH
NORTH | 15290230 | THONGPICCHETKUL LIMITED PARTNERSHIP (BR1) | NORTH
NORTHEAST | 15290115 | UBON DISTRIBUTION CO.,LTD | NORTHEAST
NORTHEAST | 15290185 | GOLD NAKHONRATCHSIMA CO.,LTD | NORTHEAST
NORTHEAST | 15290098 | UDORN ORAN (1997) PART,LTD. | NORTHEAST
NORTHEAST | 15290099 | SURIN PURITY | NORTHEAST
NORTHEAST | 15290189 | AYA INTERTRADE CO.,LTD | NORTHEAST
NORTHEAST | 15290203 | 2009 SIAMTRADING KHONKAEN CO.,LTD. | NORTHEAST
NORTHEAST | 15290218 | HIPER DC CO.,LTD. | NORTHEAST
NORTH | 15290191 | PHRAE PATTAPEE CO,LTD. | rm_user
SOUTH | 15290204 | P&Y INTERTRADE 2016 CO., LTD | SOUTH
SOUTH | 15290030 | JOBBER SURAT CO.,LTD. | SOUTH
SOUTH | 15290059 | PHI MARN CONSUMER CO.,LTD. | SOUTH
SOUTH | 15290117 | JOBBER SURAT CO,LTD. | SOUTH
SOUTH | 15290193 | GOLD 2013 CO.,LTD. | SOUTH
SOUTH | 15290216 | CHUMPHON 2000 CO., LTD | SOUTH